SHIQUE LONDON

Comprehensive SEO Implementation Plan

A merged, timeline-phased roadmap combining the SEO Audit (v2) findings with the Combined 6-Month SEO Plan

Prepared: August 11, 2026

Source documents: Shique_London_SEO_Audit_v2 · Shique_London_Combined_SEO_Plan

# Executive Summary

Shique London's core site architecture is in good shape: the homepage, services-all, about-us, contact-us, team-all, portfolio and membership pages all carry unique, well-written titles and meta descriptions, HTTPS is enabled, and a clean XML sitemap is submitted. The critical weakness sits one level down — all 13 individual treatment pages are effectively empty shells, with no body copy, no meta description, and a leftover WordPress "Hello world!" starter post still live and linked from every one of them. These are exactly the pages that should be ranking for high-intent searches like "balayage Kensington" or "keratin treatment London," and right now they have nothing for Google to rank.

Every close, comparable competitor — Sébastien Hair, Marnis Salon and GA Salons — prominently displays review counts and star ratings on their homepage and publishes original written content. Shique currently does neither. This plan closes that gap on a structured, six-month-plus timeline: it starts with a Week-1 sprint of critical, low-effort fixes pulled directly from the audit, then layers in the full technical, on-page, local, content, link-building and conversion workstreams from the Combined 6-Month SEO Plan.

### Top Priorities

- Write unique, keyword-rich copy and meta descriptions for each of the 13 service pages — the single largest missed ranking opportunity.

- Remove the leftover "Hello world!" post and default blog widget bleeding onto every service page — an easily fixed credibility issue.

- Surface reviews and star ratings on-site, and begin building location-specific content (Kensington, W14, Olympia) — every comparable competitor already does both.

- Fix technical and visibility issues (indexing, sitemap, mobile, performance) as the foundation for everything else.

- Strengthen Local SEO and citation consistency (GBP, directories, reviews) and implement structured data (LocalBusiness, Service schema).

- Build topical authority through content, then acquire local backlinks and brand mentions, and optimize the conversion funnel.

## How This Plan Is Structured

Each month below combines the phase-based tasks from the Combined 6-Month SEO Plan with the specific, evidence-based fixes identified in the SEO Audit (v2), so nothing from either source is lost and nothing is duplicated. Audit-sourced items are labeled "[Audit]" or by their audit priority/content-gap number in the task description. Every task carries a Priority (Critical / High / Medium / Low), an effort estimate, a suggested Owner role, and a Status column for tracking — fill in the Owner and Status columns with actual names and progress as work begins. Appendices at the end reproduce the audit's full keyword table, on-page issues table, technical checklist and competitor comparison for reference.

# Week 1 Sprint — Critical Fixes & Baseline Setup

These are the audit's "quick win" items (high impact, under a day of effort each) combined with the plan's Phase 0 setup tasks. Do this before anything else — most items ship this week without waiting on the rest of the roadmap.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Delete/unpublish the leftover "Hello world!" post and remove the default Recent Posts/Comments widget from the service-page template | Critical | < 1 hr | Web Developer | Not started |
| Standardize brand name to "Shique London" across footer copyright, Instagram/portfolio captions and GBP (currently reads "Stylena") | Critical | < 1 hr | Web Dev / Marketing | Not started |
| Add a true H1 to the homepage with the primary keyword (e.g. "Luxury Hair & Beauty Salon in Kensington, London") | High | 30 min | Web Developer | Not started |
| Add a homepage section showing Google/Fresha star rating and review count | High | 1–2 hrs | Web Developer | Not started |
| Write short (150–160 char) meta descriptions for all 13 service pages, ahead of the full copy rewrite | High | ~2 hrs | Copywriter / SEO Lead | Not started |
| Get/confirm access to Google Search Console, Google Analytics 4 and Google Business Profile | High | 1–2 hrs | SEO Lead | Not started |
| Verify and claim site in GSC; submit sitemap; add properties for www/non-www and http/https | High | 1 hr | SEO Lead | Not started |
| Install GA4 and link it to Search Console | High | 1 hr | SEO Lead | Not started |
| Verify Bing Webmaster Tools and enable IndexNow | Medium | 1 hr | SEO Lead | Not started |
| Snapshot current baseline metrics (organic traffic, top pages, rankings); export 3 months of historical data | High | 2 hrs | SEO Lead | Not started |
| Claim/verify Google Business Profile; ensure NAP consistency; complete all fields; upload 10+ geo-tagged photos | High | 3 hrs | Marketing / Salon Team | Not started |
| Set up a Looker Studio master dashboard (SEO & leads); schedule weekly automated GSC/GBP reports | Medium | 3 hrs | SEO Lead | Not started |

KPI / Deliverable:  Baseline dashboard live (organic sessions, impressions, clicks, position; GBP views & calls; top 10 keywords) and every Week-1 critical/high audit fix shipped.

# Month-by-Month Roadmap

## Month 1 — Technical SEO Foundation

Make the site fully crawlable, indexable, fast and mobile-friendly; close out remaining technical items flagged Fail/Warning in the audit's Technical SEO Checklist (Appendix C).

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Run a full site crawl (Screaming Frog/Sitebulb); export 4xx/5xx, redirects, duplicate titles, missing meta, large images, missing alt tags | High | Half day | SEO Lead | Not started |
| Audit site speed (PageSpeed Insights, Lighthouse, GTmetrix); run Mobile-Friendly Test — specifically test the autoplaying homepage hero video, flagged as a likely LCP/CLS risk | High | Half day | SEO Lead / Web Dev | Not started |
| Confirm SSL/HTTPS configuration remains correct (audit found this passing — verify no regressions) | Low | 15 min | Web Developer | Not started |
| Review XML sitemap footprint — audit found it currently indexes only 4 core pages + 13 service pages; plan to expand as blog/location pages launch | Medium | 30 min | SEO Lead | Not started |
| Verify robots.txt remains correctly configured (audit found this passing) | Low | 15 min | Web Developer | Not started |
| Check and fix canonical tags and hreflang settings | Medium | 1–2 hrs | Web Developer | Not started |
| Confirm no broken internal links / 4xx-5xx errors (audit found none — set up monitoring) | Medium | 1 hr | SEO Lead | Not started |
| Run mobile usability report and fix all mobile layout issues | Medium | Half day | Web Developer | Not started |
| Compress and serve images in next-gen formats (WebP) with responsive srcset; replace oversized hero assets | Medium | 1 day | Web Developer | Not started |
| Minify/combine CSS and JS, defer non-critical JS, enable browser caching and GZIP/Brotli compression | Medium | 1 day | Web Developer | Not started |
| Evaluate and configure a CDN (Cloudflare) | Medium | Half day | Web Developer | Not started |
| Spot-check structured data — audit could not confirm LocalBusiness/Service/FAQPage schema is present; verify with Google's Rich Results Test | Medium | 1 hr | SEO Lead | Not started |
| Re-run crawl and PageSpeed checks to confirm fixes; log every fix in a tracker with dates/issue references | Medium | Half day | SEO Lead | Not started |

KPI / Deliverable:  No 4xx errors on main pages; sitemap submitted; mobile score improved +10–20 points from baseline; hero-video Core Web Vitals risk validated.

## Month 2 — Keyword Research & On-Page Rewrite Sprint (Part 1)

Build the keyword foundation, then begin the audit's #1 priority: rewriting the 13 empty service pages, seven at a time.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Define seed topics: list all core and sub-services | High | 2 hrs | SEO Lead | Not started |
| Classify each keyword by intent (informational, transactional, navigational) | Medium | 2 hrs | SEO Lead | Not started |
| Research 50+ local keywords (Ahrefs/SEMrush/Ubersuggest) — use the audit's Keyword Opportunity Table (Appendix A) as the starting seed list | High | 1 day | SEO Lead | Not started |
| Add London-based local modifiers ("in London", "Kensington", "near me") | Medium | 2 hrs | SEO Lead | Not started |
| Group keywords into clusters by service type | Medium | Half day | SEO Lead | Not started |
| Analyze the audit's three closest competitors — Sébastien Hair, Marnis Salon, GA Salons — via Ahrefs Site Explorer; identify content gaps | High | 1 day | SEO Lead | Not started |
| Prioritize keywords by volume/difficulty/local intent; segment into Tier 1/2/3 | Medium | Half day | SEO Lead | Not started |
| Build a keyword mapping sheet (Page URL, Primary/Secondary Keyword, Volume, Intent, Difficulty); assign one focus keyword per page | High | 1 day | SEO Lead | Not started |
| Set up Ahrefs/Ubersuggest for ongoing backlink tracking | Low | 1 hr | SEO Lead | Not started |
| AUDIT PRIORITY #1 — Write unique 150–300 word body copy + meta description for the first 7 of 13 service pages (Full Head Highlights, Airtouch, Tokio Inkarami, Japanese Manicure, Russian Manicure, Brow Lamination, Lash Extensions) | Critical | Multi-day | Copywriter + SEO Lead | Not started |
| Rewrite service page titles to add a location modifier (e.g. "Full Head Highlights in Kensington, London ¦ Shique London") | High | Half day | Copywriter | Not started |
| Quick win — Launch a bridal/occasion hair & makeup package landing page (no competitor-equivalent gap identified in the audit) | High | Half day | Web Dev + Copywriter | Not started |

KPI / Deliverable:  7 of 13 service pages fully rewritten with unique copy, meta descriptions and location-modified titles; keyword map complete; bridal/occasion page live.

## Month 3 — On-Page Completion, Structured Data & Local SEO

Finish the remaining service pages, implement schema, and build out local trust signals — citations, reviews and the first location landing page.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Complete unique body copy + meta descriptions for the remaining 6 of 13 service pages | Critical | Multi-day | Copywriter + SEO Lead | Not started |
| Add FAQ sections (6–8 Qs per service) with FAQPage schema; trim the FAQ block currently duplicated verbatim across 17+ pages down to 1–2 hub pages | Medium | 1 day | Copywriter / Web Dev | Not started |
| Add visible opening hours + LocalBusiness schema on Contact Us (audit found NAP not marked up beyond the map embed) | Medium | 2 hrs | Web Developer | Not started |
| Add internal links between service pages, blog and homepage using keyword-rich anchor text | Medium | Half day | SEO Lead | Not started |
| Add descriptive alt text to Portfolio images (currently embedded Instagram posts with no independent alt text) and compress sitewide | Low | Half day | Web Developer | Not started |
| Add one keyword-relevant specialty phrase to each stylist bio (e.g. "balayage specialist") | Low | 1 hr | Copywriter | Not started |
| Improve CTA placement and design across pages | Medium | Half day | Web Developer | Not started |
| Implement LocalBusiness, Service and Breadcrumb schema (JSON-LD); validate with Google's Rich Results Test | Medium | Half day | Web Developer | Not started |
| Run a content gap analysis against the top 3 competitors to guide future updates | Medium | Half day | SEO Lead | Not started |
| Audit NAP citations and fix inconsistencies across GBP, footer and directories | High | Half day | Marketing | Not started |
| List the business on Yell, Yelp, ThomsonLocal, Treatwell, Fresha, Bing Places, FreeIndex (BrightLocal/Whitespark); 100% NAP consistency | High | 1 day | Marketing | Not started |
| Embed a Google Map on the Contact and homepage | Low | 1 hr | Web Developer | Not started |
| Content gap #1 — Build a Kensington/W14 location landing page with schema and internal links to services | High | 1 day | Copywriter + Web Dev | Not started |
| Stand up a review-request system (WhatsApp/email/SMS/in-salon) after every appointment; target 10–20 new reviews; respond to every review | High | Ongoing | Salon Team / Marketing | Not started |
| Add aggregateRating schema once review volume supports it | Medium | 1 hr | Web Developer | Not started |
| Publish weekly GBP posts (offers, trends, availability); monitor and answer GBP Q&A | Medium | Ongoing | Marketing | Not started |

KPI / Deliverable:  All 13 service pages complete; structured data implemented and validated; NAP citations 80%+ consistent; Kensington/W14 location page live; review-request flow active.

## Month 4 — Content Production & Topical Authority

Launch the blog/journal properly (replacing the default WordPress post), publish the audit's ready-made differentiation content, and expand location and membership pages.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Build keyword/content clusters (colour services, bridal, nails, lash lifts) mapped to content type | Medium | 1 day | SEO Lead | Not started |
| Build a rolling content calendar (min. 2–3 posts/month, 3 months out) plus quarterly service-page refreshes | Medium | 1 day | Content Lead | Not started |
| Content gap #5 — Launch a proper monthly blog/journal section, fully replacing the default WordPress starter post | High | Ongoing | Content Lead | Not started |
| Write one pillar guide (2,000+ words) linking to relevant service pages | Medium | 1–2 days | Copywriter | Not started |
| Content gap #3 — Publish the ready-made differentiation posts: "What is Airtouch?", "Tokio Inkarami vs Keratin Treatment", "Balayage vs Highlights" (5+ posts total, 800–1,200 words each) | High | 1–2 hrs/post | Copywriter | Not started |
| Build a second location content page (Notting Hill or Chelsea) with embedded map and local landmarks | Medium | 1 day | Copywriter + Web Dev | Not started |
| Structure posts for featured snippets (definitions, numbered steps, comparison tables) | Low | Ongoing | Copywriter | Not started |
| Add optimized images, before/after galleries, and Article/FAQ schema to new content | Medium | Ongoing | Web Developer | Not started |
| Create shareable assets: an infographic and a downloadable PDF guide/lookbook | Low | 1–2 days | Design / Marketing | Not started |
| Content gap #6 — Expand the membership page with full terms, a membership-specific FAQ, and member testimonials | Medium | 1–2 hrs | Copywriter | Not started |
| Internal-link new content to service pages; promote via GBP posts, Instagram and Facebook; boost top performers | Medium | Ongoing | Marketing | Not started |
| Final QA — confirm every image sitewide is compressed with descriptive, keyword/location-aware alt text | Low | Half day | Web Developer | Not started |

KPI / Deliverable:  6–9+ quality content pieces published; improved rankings for long-tail queries (positions 4–20); monthly blog cadence established.

## Month 5 — Link Building, PR, Partnerships & Conversion Optimization

Acquire localized, high-quality links and brand mentions, then turn the traffic gains into bookings.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Audit existing backlinks (Ahrefs/SEMrush); analyze the 3 local competitors for link opportunities | Medium | 1 day | SEO Lead | Not started |
| Use Ahrefs Link Intersect to find competitor backlink sources; build a 10–15 site outreach target list | Medium | 1 day | SEO Lead | Not started |
| Identify targets: local blogs/lifestyle magazines, wedding planners/bridal directories, beauty micro-influencers, cross-promo partners | Medium | 1 day | Marketing | Not started |
| Draft value-first outreach templates (free styling for shoots, guest posts, partner discounts) | Low | Half day | Marketing | Not started |
| Reach out to 5–10 local businesses for cross-promotion; pitch 1–2 guest posts/month; contact local influencers | Medium | Ongoing | Marketing | Not started |
| Create outreach-bait resources: a Local Vendor/Wedding Guide, an ultimate guide (1,500+ words), shareable infographics | Low | 1–2 days | Content Lead | Not started |
| Track outreach responses; log every placed link (URL, DR/DA, referral traffic); monitor new referring domains | Low | Ongoing | SEO Lead | Not started |
| Search for unlinked brand mentions and request a link | Low | 2 hrs | SEO Lead | Not started |
| Pursue local press/editorial coverage, following the model GA Salons and Hiro Miyoshi use for authority-building | Medium | Ongoing | Marketing / PR | Not started |
| Map the user journey (organic landing → service page → Fresha booking); find drop-off points via GA4 funnels or session recordings | High | 1 day | SEO Lead | Not started |
| Strengthen CTAs — "Book Now" above the fold, click-to-call, WhatsApp deep link, urgency messaging; test full booking journey | High | 1 day | Web Developer | Not started |
| Resolve any remaining broken links via GSC/Screaming Frog with 301 redirects | Low | 2 hrs | Web Developer | Not started |
| Address remaining performance issues (server response time, render-blocking resources, heavy theme elements) | Medium | 1 day | Web Developer | Not started |
| Launch localized paid search / GBP Local Services ads for high-intent keywords with GA4 conversion tracking | Medium | 1 day | Marketing | Not started |
| Set up a retargeting audience (Google Ads/Meta) for service-page visitors who didn't book | Low | Half day | Marketing | Not started |
| Add membership/loyalty content to site navigation, optimized for related searches | Low | 2 hrs | Web Developer | Not started |

KPI / Deliverable:  +10–20 new quality referring domains; 2+ local editorial mentions or partnerships; improved booking conversion rate vs. baseline; +20–30 new Google reviews.

## Month 6 — Second-Pass Technical Validation, Reporting & Next-Cycle Roadmap

Re-validate technical health once traffic and content volume have grown, consolidate results, and hand off repeatable processes.

| Task | Priority | Effort | Owner | Status |
| --- | --- | --- | --- | --- |
| Re-run a full crawl (Screaming Frog) and fix any newly surfaced issues | Medium | Half day | SEO Lead | Not started |
| Re-check mobile and desktop speed scores against the Month 0 baseline | Medium | Half day | SEO Lead | Not started |
| Implement lazy loading for images | Low | 2 hrs | Web Developer | Not started |
| Minify CSS/JS/HTML (e.g. WP Rocket) | Low | 2 hrs | Web Developer | Not started |
| Finalize CDN setup (Cloudflare) for faster global delivery | Low | 2 hrs | Web Developer | Not started |
| Confirm browser caching and GZIP/Brotli compression are active sitewide | Low | 1 hr | Web Developer | Not started |
| Produce a full-period SEO report: traffic growth, keyword rankings, GBP impressions/actions, backlinks gained, technical fixes, speed | High | 1 day | SEO Lead | Not started |
| Compare Month 0 baseline to current data: organic clicks (GSC), map views/calls (GBP), top-10 keyword movement, conversions (GA4) | High | 1 day | SEO Lead | Not started |
| Review all KPIs; re-evaluate keyword priorities based on actual performance | Medium | Half day | SEO Lead | Not started |
| Identify top-performing keywords/pages to scale further; run a fresh competitor backlink gap analysis | Medium | 1 day | SEO Lead | Not started |
| Run A/B tests on high-impact elements (homepage hero, CTA buttons) | Low | Ongoing | Web Developer | Not started |
| Double down on content formats that worked; consider a newsletter sign-up to capture repeat visitors | Low | Half day | Content Lead | Not started |
| Establish ongoing SOPs: weekly GBP/review management, monthly blog post, quarterly technical/citation audit; document each process | High | 1 day | SEO Lead | Not started |
| Plan the next cycle: new neighbourhoods/service areas, video (YouTube), visual search optimization, updated content/link roadmap | Medium | 1 day | SEO Lead | Not started |

KPI / Deliverable:  Steady organic growth and improved local visibility documented against the Month 0 baseline; SOPs and next-cycle roadmap handed off.

# Recommended Tools & Providers

- Tracking & Reporting: Google Search Console, Google Analytics 4, Looker Studio

- Site Audit & Crawling: Screaming Frog, Sitebulb

- Performance: PageSpeed Insights, Lighthouse, GTmetrix, WP Rocket, Cloudflare (CDN & caching)

- Keyword & Backlink Research: Ahrefs, SEMrush, Ubersuggest

- Local SEO & Citations: BrightLocal, Whitespark, Google Business Profile

- Content Optimization: SurferSEO, Clearscope, Grammarly

- Image Optimization: TinyPNG, ShortPixel

- WordPress SEO Plugin: Rank Math or All in One SEO (AIOSEO is already in use per the audit)

- Conversion tracking / UX: Hotjar or FullStory for session recordings and funnel drop-off analysis

# Ongoing Cadence (Post-Month 6)

- Weekly: GBP posts and review responses

- Monthly: one new blog/journal post

- Quarterly: full technical health check (GSC/crawl) and citation/link audit

- Quarterly: service-page content refresh

Document each of the above as a step-by-step SOP so the cadence survives staff or agency changes.

# Appendix A — Keyword Opportunity Table

Estimated from competitive positioning and search-landscape research (no Ahrefs/SEMrush was connected for the original audit — connect an SEO tool for precise volume and difficulty data). Full table of 20+ keywords is in the source audit; the highest-priority subset is reproduced here.

| Keyword | Difficulty | Opportunity | Ranking | Recommended Content |
| --- | --- | --- | --- | --- |
| hair salon Kensington | Hard | High | Not ranking | Optimize homepage + new Kensington location page |
| hair salon W14 | Easy | High | Not ranking | Location page targeting W14/Olympia |
| balayage Kensington | Moderate | High | Not ranking | Full-head-highlights / balayage page rewrite |
| Airtouch hair Kensington | Easy | High | Not ranking | Rewrite /services/airtouch/ with full copy |
| Tokio Inkarami London | Easy | High | Not ranking | Rewrite /services/tokio-inkarami/ page |
| keratin treatment London | Moderate | Medium | Not ranking | Keratin/smoothing service page copy |
| Japanese manicure London | Easy | High | Not ranking | Rewrite /services/japanese-manicure/ page |
| Russian manicure Kensington | Moderate | Medium | Not ranking | Manicure page + comparison content |
| brow lamination Kensington | Easy | Medium | Not ranking | Rewrite /services/brow-lamination/ page |
| lash extensions Kensington | Moderate | Medium | Not ranking | Rewrite /services/lash-extensions/ page |
| bridal hair and makeup Kensington | Moderate | High | No page exists | New bridal/occasion package page |
| what is Airtouch hair colouring | Easy | Medium | No content | Blog post: Airtouch vs balayage |
| Tokio Inkarami vs keratin treatment | Easy | Medium | No content | Blog/comparison post |
| balayage vs highlights | Easy | Medium | No content | Blog post (broad top-of-funnel) |
| nail salon Kensington SW7 | Moderate | Medium | Not ranking | Nails page with location keyword |
| hair salon near Olympia | Easy | Medium | Not ranking | W14/Olympia location page |
| best hair salon Kensington | Hard | Medium | Not ranking | Needs review volume, then homepage opt. |
| luxury hair salon London | Hard | Low | Not ranking | Long-term brand-authority target |

# Appendix B — On-Page Issues Reference

| Page | Issue | Severity | Recommended Fix |
| --- | --- | --- | --- |
| All 13 /services/* pages | No body copy, no meta description — content is essentially blank aside from title and booking button | Critical | Write unique 150–300 word copy + custom meta description per page |
| All 13 /services/* pages | Default WordPress "Recent Posts/Comments" widget shows the leftover "Hello world!" post on every page | Critical | Delete the post; remove the widget from the template |
| Homepage | No true H1 — the top heading renders as an H2 | High | Add an H1 with the primary keyword |
| Footer / Portfolio / Instagram | Brand inconsistency: "© Stylena 2026" and "#StylenaSalon" vs. "Shique London" elsewhere | High | Standardize brand name sitewide |
| All 13 /services/* pages | Titles have no location modifier | Medium | Rewrite as "[Service] in Kensington, London ¦ Shique London" |
| Site-wide (17+ pages) | Identical FAQ block duplicated verbatim across nearly every page | Medium | Keep full FAQ on 1–2 hub pages with FAQPage schema; trim elsewhere |
| Contact Us | No visible opening hours; NAP not marked up as structured data | Medium | Add visible hours + LocalBusiness schema |
| Portfolio | Entirely embedded Instagram posts; no independent alt text | Low | Add descriptive alt text to portfolio images |
| Team | Stylist bios don't mention searchable specialties | Low | Add one keyword-relevant phrase per bio |

# Appendix C — Technical SEO Checklist (Audit Baseline)

| Check | Status | Details |
| --- | --- | --- |
| HTTPS | Pass | Site fully served over HTTPS with self-referencing canonicals |
| Robots.txt | Pass | Present and correctly configured; references both sitemap files |
| XML sitemap | Pass* | Present via AIOSEO, but only indexes 4 core pages + 13 service pages — small footprint to expand |
| Mobile viewport | Pass | Correct viewport meta tag present on all pages checked |
| Meta robots / indexation | Pass | No pages incorrectly blocked; "Hello world!" post correctly set to noindex |
| Title tags (core pages) | Pass | Homepage, services-all, about, contact, team, portfolio, membership all unique & keyword-rich |
| Title tags (service pages) | Fail | All 13 /services/* pages use generic titles with no location keyword |
| Meta descriptions (core pages) | Pass | Present and well-written on all top-level pages |
| Meta descriptions (service pages) | Fail | None of the 13 service pages have a meta description |
| H1 structure | Warning | Homepage lacks a true H1; other checked pages each have one H1 |
| Duplicate content | Warning | Identical FAQ block repeated across 17+ pages |
| Legacy CMS content exposed | Fail | "Hello world!" post and default commenter still live and linked from every service page |
| Structured data | Warning | Not independently verified — AIOSEO typically adds baseline schema; confirm with Rich Results Test |
| Image alt text | Warning | Not fully verifiable via crawl; recommend manual check, especially Portfolio/Services |
| Page speed / Core Web Vitals | Warning | Not measured in audit; autoplaying hero video is a likely LCP/CLS risk |
| Broken links | Pass | No broken links found across primary navigation and pages checked |

# Appendix D — Competitor Comparison Summary

The three closest positioning matches — same postcode area, same luxury-boutique tier, similar service mix.

| Dimension | Shique London | Sébastien Hair | Marnis Salon | GA Salons |
| --- | --- | --- | --- | --- |
| Service page content depth | Thin — no body copy | Full descriptions + pricing | Full descriptions + pricing | Long-form, brand-driven copy |
| Reviews shown on-site | None (off-site link only) | 4.9★, 1,958 reviews on homepage | Full testimonial wall | 4.9★, 1,404 reviews + press logos |
| Location pages | 1 (generic) | 1 (detailed neighbourhood) | 1 (detailed) | 6 (multi-neighbourhood + intl.) |
| Blog / content marketing | None (default post only) | None | "Journal" section | "Blog" + national press coverage |
| Bridal/occasion package page | None | Yes (Occasion Styling) | None | Yes (Bridal) |
| Brand consistency | Inconsistent (Stylena vs Shique) | Consistent | Consistent | Consistent |

Other submitted competitors — Michaeljohn Salon & Medispa, Daniel Galvin, Hiro Miyoshi, Kensington Glam, LY Beauty and Oblique — sit either above Shique on scale/heritage or at a similar boutique tier with comparable gaps. Note: hk-london.com was excluded as a City of London real estate consultancy, not a salon.